## Component Migration Map
Old Component | Category | Variants / Props | Used In (Flows / Screens) | Change Type | New Component Destination | Status | Notes
NAVIGATION & LAYOUT
Header | Navigation | Breakpoint: Mobile/Desktop State: ANON/Member/Exit/Breadcrumb/Title/Branded-light/Branded-dark (9 variants) | All flows — Core flows, Review+Payment, Viator, Promocode | TBD | TBD | Not started | Primary nav bar; responsive
Side menu (Desktop) | Navigation | Persona: ANON/Member State: Open/Close (4 variants) | Core flows, UI skinning | TBD | TBD | Not started | Desktop slide-out menu
Side menu (Mobile) | Navigation | State: Guest/Member (2 variants) | Core flows (mobile) | TBD | TBD | Not started | Mobile drawer menu
Side menu (Page components) | Navigation | Log in / Variant2 (2 variants) | Core flows — page components section | TBD | TBD | Not started | Auth-specific side menu variant
Side menu/Sign up | Navigation | Standalone component | Core flows — page components | TBD | TBD | Not started
nav link | Navigation | State: Default/Hover (2 variants) | Core flows, UI skinning | TBD | TBD | Not started | Duplicated in UI skinning page
Logo-horizontal | Branding | Default / Variant2 (2 variants) | Core flows — header area | TBD | TBD | Not started
Company Logo | Branding | Alternate: True/False (2 variants) | Design system — Logos frame; used in all page headers | TBD | TBD | Not started | Primary logo mark
Fixed CTA | Layout | Type: Trip/Flights/Type3/Cart (4 variants) | Core flows — booking & itinerary | TBD | TBD | Not started | Sticky bottom action bar
Bottom drawer | Layout | Type: Cart/Info State: Open/Closed Steps: 3/4 (11 variants) | Review + Payment (2026) | TBD | TBD | Not started | Mobile bottom sheet / drawer
Side section | Layout | 5 variants (Default + 4) | Review + Payment (2026) | TBD | TBD | Not started | Desktop sidebar panel
BUTTONS & ACTIONS
Button | Action | Style: Primary/Secondary/Tertiary/Link Size: Small/Medium Icon position: No icon/Leading/Trailing/Only State: Default/Hover/Disabled/With 3rd party (68 variants) | All flows — universal component | TBD | TBD | Not started | Core button system; design system page
Button/Secondary/Medium (orphan) | Action | Disabled state only (1 standalone variant) | UI base components page | TBD | TBD | Not started | Outside main Button component set — may be stale
Filter component | Action | State: Selected/Unselected (2 variants) | UI base components; Core flows (search/browse) | TBD | TBD | Not started | Chip-style filter toggle
Filter | Action | Default / Filter on (2 variants) | Core flows — search results | TBD | TBD | Not started | Filter panel or indicator (separate from Filter component)
FORM CONTROLS
Text Input | Form | Size: Large/Medium State: Default/Inputted/Error Button: Yes/No (~8 variants) | UI base components; Review+Payment forms | TBD | TBD | Not started
Text Area | Form | Documented in UI Elements frame (not a component set) | UI base components | TBD | TBD | Not started | May need to be promoted to component
Select | Form | Documented in UI Elements frame (not a component set) | UI base components | TBD | TBD | Not started | Dropdown select; may need to be promoted
Checkbox | Form | Selected: True/False Alternate: False (2 variants) | UI base components; booking forms | TBD | TBD | Not started
Stepper | Form | Single component (no variants) | UI base components — inputs section | TBD | TBD | Not started | Numeric +/- stepper
Item (Dropdown) | Form | Default / Hover (2 variants) | UI base components — inputs section | TBD | TBD | Not started | Dropdown list item
Chat input | Form | Type: Default/Secondary/Inputted/Disabled/Stop answer (5 variants in DS) Also 3-variant version in Core flows | UI base components; Core flows — Zoya chat | TBD | TBD | Not started | AI chat text input; two versions exist
Selection | Form | 2 variants | Itinerary collaboration (2026) | TBD | TBD | Not started | Selection control for itinerary
TABS & NAVIGATION PATTERNS
Tab component | Navigation | Size: Small/Medium/Line State: Default/Border/Hover (~8 variants) | UI base components; Viator detail pages | TBD | TBD | Not started
Tab group | Navigation | Bordered / No border / Line (3 variants) | UI base components; Core flows | TBD | TBD | Not started | Container for tab components
With icon Tab component | Navigation | 2 states (hover / not hover) | UI base components — displayed as instances | TBD | TBD | Not started | Tab with leading icon
CARDS & CONTENT BLOCKS
Itinerary card | Card | Default / Hover (2 variants) | Core flows — My Trips / history | TBD | TBD | Not started
Itinerary item | Card | State: Closed/Open/State3 (3 variants) | Core flows — itinerary day view | TBD | TBD | Not started | Expandable itinerary activity
Event card | Card | Morning/Afternoon/2 activities/Evening (4 variants) | Core flows — itinerary timeline | TBD | TBD | Not started | Time-of-day event grouping
Location card | Card | Default / Hover (2 variants) | Core flows — destination browsing | TBD | TBD | Not started
Hotel list item | Card | User: ANON/Member (2 variants) | Core flows — hotel search results | TBD | TBD | Not started
Info card | Card | Type: Traveler/Payment/Stay/Flight Traveler: 1/2 State: many (25 variants) | Review + Payment (2026) | TBD | TBD | Not started | Complex card with many state combos
Traveler card-info block | Card | Closed: Default/Open (2 variants) | Review + Payment (2026) | TBD | TBD | Not started | Expandable traveler info
Review Card | Card | Frame (not a component) | Viator — activity detail | TBD | TBD | Not started | User review display; consider promoting
Benefit banner | Card | Security/Call/Refund/Variant4 (4 variants) | Review + Payment (2026) | TBD | TBD | Not started | Trust/benefit messaging strip
BOOKING & TRAVEL
Booking section (Search) | Booking | Type: Trip/Trip-multi city/Flight/Stay State: Default/Hover Breakpoint: Mobile/Desktop (10 variants) | Core flows — search/booking entry | TBD | TBD | Not started | Search form sections
Booking section (Edit) | Booking | Type: Flights/Stays Progress: Edit State: Open/Closed Route: Round/One-way/Multi-city Breakpoint: Mobile/Desktop (7 variants) | Core flows — edit booking details | TBD | TBD | Not started | Edit mode booking panels
Flight line | Booking | Breakpoint: Desktop/Mobile (2 variants) | Core flows — flight results | TBD | TBD | Not started | Single flight result row
List item (Flight) | Booking | Breakpoint: Mobile/Desktop State: Close/Added to cart User: Member (4 variants) | Core flows — flight list | TBD | TBD | Not started
Flight details | Booking | Type: Flights/Stay Content: Route/Fare Breakpoint: Mobile/Desktop (4 variants) | Core flows — flight/stay detail panels | TBD | TBD | Not started
Benefits | Booking | Default/Included/Not included (3 variants) | Core flows — fare comparison | TBD | TBD | Not started | Fare benefit checklist
Cart | Booking | State: Default/Filled (2 variants) | Core flows — header cart icon | TBD | TBD | Not started | Cart indicator/badge
Time Selector | Booking | State: Default/Selected/Hover/Disabled Seats: All/Few/AlmostNone Popular: true/false (7 variants) | Viator — activity booking | TBD | TBD | Not started | Time slot picker for activities
Price sticky banner | Booking | State: Closed/Open (2 variants) | Promocode (2025) | TBD | TBD | Not started | Sticky price bar with promo
Promocode | Booking | Open / Closed (2 variants) | Review + Payment (2026) | TBD | TBD | Not started | Promo code entry section
Check icon | Booking | Fulfilled/Unfulfilled/Number (3 variants) | Review + Payment (2026) | TBD | TBD | Not started | Step/checklist status icon
CHAT & AI (ZOYA)
Chat bubble (Zoya) | Chat | Person: Zoya/You Type: Latest/Old/1 line/2 line/Suggestion (5 variants) | Core flows — Zoya chat (mobile) | TBD | TBD | Not started | Mobile chat messages
Chat bubble (Desktop) | Chat | 1 line / 2 lines / No bg (3 variants) | Core flows — Zoya chat (desktop) | TBD | TBD | Not started | Desktop chat messages
Chat bubble-1 | Chat | 6 variants (Default + 5) | Core flows — chat animations | TBD | TBD | Not started | Animated chat bubble sequence
Chat bubble-2 | Chat | 6 variants (Default + 5) | Core flows — chat animations | TBD | TBD | Not started | Second animated bubble sequence
Blinking fox | Chat | 3 blink animation states | Core flows — Zoya mascot | TBD | TBD | Not started | Zoya fox avatar animation frames
FEEDBACK & STATUS
Toast | Feedback | State: Success/Error/Info (3 variants) | UI base components; likely used across flows | TBD | TBD | Not started
Star | Feedback | Filled / Unfilled (2 variants) | Core flows — hotel ratings | TBD | TBD | Not started | Star rating component
Indicator | Feedback | Selected / Unselected (2 variants) | Core flows — pagination/carousel dots | TBD | TBD | Not started
Progress bar | Feedback | start / filled (2 variants) | Core flows — onboarding/loading | TBD | TBD | Not started
Page loader | Feedback | 1 variant | Core flows — page transitions | TBD | TBD | Not started | Full-page loading state
Budget meter | Feedback | Default / Variant2 (2 variants) | Itinerary collaboration (2026) | TBD | TBD | Not started | Budget progress indicator
AVATARS & MEDIA
Avatar | Media | Size: Large/Medium/Small (3 variants) | UI base components; chat, user profiles | TBD | TBD | Not started
Bg (Backgrounds) | Media | 5 variants | Core flows — hero/landing sections | TBD | TBD | Not started | Decorative background patterns
List item (generic) | Content | Default / Variant2 (2 variants) | Core flows | TBD | TBD | Not started | Generic list row
Frame 566 (unnamed) | Content | Default / Variant2 (2 variants) | Review + Payment (2026) | TBD | TBD | Not started | Needs a proper name — audit for purpose
ICONS
Material Icons library | Icons | ~3,635 icon components (Material Design) | All flows — universal | TBD | TBD | Not started | Large icon set; audit which are actually used

## Design Tokens
Token Category | Token Name (Figma Style) | Current Value | New Value | Status
TYPOGRAPHY — Heading Styles
Typography | Heading/H1 | Inter Bold 56px / 120% line-height | TBD | Not started
Typography | Heading/H2 | Inter Bold 48px / 120% | TBD | Not started
Typography | Heading/H3 | Inter Bold 40px / 120% | TBD | Not started
Typography | Heading/H4 | Inter Bold 38px / 130% | TBD | Not started
Typography | Heading/H5 | Inter Bold 28px / 140% | TBD | Not started
Typography | Heading/H6 | Inter Bold 24px / 140% | TBD | Not started
Typography | Heading/Tagline | Satoshi Medium 16px / 150% | TBD | Not started
TYPOGRAPHY — Body Text Styles
Typography | Text/Large/Light | Inter Light 24px / 140% | TBD | Not started
Typography | Text/Large/Normal | Inter Regular 24px / 140% | TBD | Not started
Typography | Text/Large/Medium | Inter Medium 24px / 140% | TBD | Not started
Typography | Text/Large/Semi Bold | Inter Semi Bold 24px / 140% | TBD | Not started
Typography | Text/Large/Bold | Inter Bold 24px / 140% | TBD | Not started
Typography | Text/Large/Extra Bold | Inter Extra Bold 24px / 140% | TBD | Not started
Typography | Text/Large/Link | Inter Regular (underlined) 24px / 140% | TBD | Not started
Typography | Text/Medium/Light | Inter Light 22px / 140% | TBD | Not started
Typography | Text/Medium/Normal | Inter Regular 22px / 140% | TBD | Not started
Typography | Text/Medium/Medium | Inter Medium 22px / 140% | TBD | Not started
Typography | Text/Medium/Semi Bold | Inter Semi Bold 22px / 140% | TBD | Not started
Typography | Text/Medium/Bold | Inter Bold 22px / 140% | TBD | Not started
Typography | Text/Medium/Extra Bold | Inter Extra Bold 22px / 140% | TBD | Not started
Typography | Text/Medium/Link | Inter Regular (underlined) 22px / 140% | TBD | Not started
Typography | Text/Regular/Light | Inter Light 20px / 140% | TBD | Not started
Typography | Text/Regular/Normal | Inter Regular 20px / 140% | TBD | Not started
Typography | Text/Regular/Medium | Inter Medium 20px / 140% | TBD | Not started
Typography | Text/Regular/Semi Bold | Inter Semi Bold 20px / 140% | TBD | Not started
Typography | Text/Regular/Bold | Inter Bold 20px / 140% | TBD | Not started
Typography | Text/Regular/Extra Bold | Inter Extra Bold 20px / 140% | TBD | Not started
Typography | Text/Regular/Link | Inter Regular (underlined) 20px / 140% | TBD | Not started
Typography | Text/Small/Light | Inter Light 18px / 140% | TBD | Not started
Typography | Text/Small/Normal | Inter Regular 18px / 140% | TBD | Not started
Typography | Text/Small/Medium | Inter Medium 18px / 140% | TBD | Not started
Typography | Text/Small/Semi Bold | Inter Semi Bold 18px / 140% | TBD | Not started
Typography | Text/Small/Bold | Inter Bold 18px / 140% | TBD | Not started
Typography | Text/Small/Extra Bold | Inter Extra Bold 18px / 140% | TBD | Not started
Typography | Text/Small/Link | Inter Regular (underlined) 18px / 140% | TBD | Not started
Typography | Text/Tiny/Light | Inter Light 16px / 140% | TBD | Not started
Typography | Text/Tiny/Normal | Inter Regular 16px / 140% | TBD | Not started
Typography | Text/Tiny/Medium | Inter Medium 16px / 140% | TBD | Not started
Typography | Text/Tiny/Semi Bold | Inter Semi Bold 16px / 140% | TBD | Not started
Typography | Text/Tiny/Bold | Inter Bold 16px / 140% | TBD | Not started
Typography | Text/Tiny/Extra Bold | Inter Extra Bold 16px / 140% | TBD | Not started
Typography | Text/Tiny/Link | Inter Regular (underlined) 16px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Light | Inter Light 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Normal | Inter Regular 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Medium | Inter Medium 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Semi Bold | Inter Semi Bold 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Bold | Inter Bold 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Extra Bold | Inter Extra Bold 14px / 140% | TBD | Not started
Typography | Text/Extra Tiny/Link | Inter Regular (underlined) 14px / 140% | TBD | Not started
TYPEFACES
Typeface | Heading Typeface | Satoshi (referenced) / Inter Bold (actual) | TBD | Not started
Typeface | Body Typeface | Inter | TBD | Not started
Typeface | Lato specimens | Lato (19 weight specimens on Style page) | TBD | Not started
Typeface | Inter specimens | Inter (19 weight specimens on Style page) | TBD | Not started
COLORS — Brand
Color | Primary Purple | #6c00f6 | TBD | Not started
Color | Accent Green | #a1f919 | TBD | Not started
Color | Accent Blue | #00b8ff | TBD | Not started
COLORS — Neutrals
Color | White | #ffffff | TBD | Not started
Color | Gray-100 | #eeeeee | TBD | Not started
Color | Gray-200 | #cccccc | TBD | Not started
Color | Gray-300 | #aaaaaa | TBD | Not started
Color | Gray-400 | #666666 | TBD | Not started
Color | Gray-500 | #444444 | TBD | Not started
Color | Gray-600 | #222222 | TBD | Not started
Color | Black | #000000 | TBD | Not started
SHADOWS (Effect Styles)
Shadow | xxsmall | drop-shadow 0 1px 2px rgba(0,0,0,0.05) | TBD | Not started
Shadow | xsmall | drop-shadow 0 1px 2px rgba(0,0,0,0.06) + 0 1px 3px rgba(0,0,0,0.10) | TBD | Not started
Shadow | small | drop-shadow 0 2px 4px rgba(0,0,0,0.06) + 0 4px 8px rgba(0,0,0,0.10) | TBD | Not started
Shadow | medium | (defined in file — values truncated in scan) | TBD | Not started
Shadow | large | (defined in file — values truncated in scan) | TBD | Not started
Shadow | xlarge | (defined in file — values truncated in scan) | TBD | Not started
Shadow | xxlarge | (defined in file — values truncated in scan) | TBD | Not started
BORDER RADIUS
Radius | Radius tokens | 4 groups documented on Style page (values in Figma variables) | TBD | Not started

## Summary
Metric | Count | Notes
Component Sets (with variants) | 57 | Across all pages in the file
Standalone Components (not in a set) | ~3,900+ | Mostly Material Icons (~3,635)
Component Sets in Design System pages | 10 | Button, Filter, Tab, Tab group, Checkbox, Avatar, Chat input, Text Input, Item, Toast
Component Sets in Core Flows | 28 | Header, Side menu, Chat, Booking, Cards, etc.
Component Sets in 2026 pages | 9 | Review+Payment & Itinerary collaboration
Component Sets in other pages | 4 | Promocode, Viator, UI skinning
Text Styles defined | 49 | H1-H6 + Tagline + 6 sizes × 7 weights
Effect Styles (Shadows) | 7+ | xxsmall through xxlarge
Paint Styles defined | 0 | No local paint styles — colors are in variables or inline
Brand Colors | 3 | Purple #6c00f6, Green #a1f919, Blue #00b8ff
Neutral Colors | 8 | White through Black (8-step scale)
Icon Components | ~3,635 | Material Design icon library
Total rows in migration map |  | All components have a row — nothing should be missed